## Progress of MH Standard 1
Target for evaluation strategy
Has not commenced/ behind target
Progressing well, on target
Completed / target achieved
Recommendation | Planned Actions | Evaluation Strategy | Progress updates
|  |  | 2018-03-23 | 2018-03-30 | 2018-04-06 | 2018-04-13 | 2018-04-20 | 2018-04-27 | 2018-05-04 | 2018-05-11 | 2018-05-18 | 2018-05-25 | 2018-06-01 | 2018-06-08 | 2018-06-15
1.2.2 Action is taken to improve the safety and quality of patient care | Ensure that action is taken to improve the safety and quality of patient care by adhering to the Mental Health Act of South Australia in the use of Seclusion Rooms in the Emergency Departments of the Royal Adelaide Hospital and the Queen Elizabeth Hospital. | Plan is to be developed to outline the planned actions to be taken including responsibility and timeframes - the plan should identify if there is a procedure in place on seclusion practices in the ED
| ED seclusion rooms to be altered so as not lock automatically. | 100% of ED seclusion rooms will not lock automatically
| Rates of restraint and seclusion in ED to be monitored | Point prevalance survey of restraint and seclusion to be conducted
SLS reporting of restraint & seclusion incidents in ED to increase by 50%.
| RAH and TQEH ED staff will be provided with education regarding restraint and seclusion, MH Act, criteria that includes continuous observation (seclusion, mechanical restraint). | 100% of RAH and TQEH ED staff will be provided with education regarding restraint and seclusion
| Meeting to discuss Toxicology Pathway Model of Care or presentations with acute drug and alcohol presentations to be held between ED & MH | A strategy is developed for patients presentating to ED with drug and alcohol issues
| Toxicology Pathway Model of Care or presentations with acute drug and alcohol presentations to be developed | Toxicology Pathway Model of Care or presentations with acute drug and alcohol presentations to be developed
| Revise exisiting procedures (OWI, SSI) regarding restraint and seclusion in ED | Revised preocedure will include the responsibility restaint and seclusion of MH clients in ED
One action from the action plan to be implemented and evaluated
100% compliance with Mental Health Act in ED regarding restaint and seclusion -
| Working group is in place to address the length of stay of Mental Health patient's in ED | No MH ED consumer to remain in ED > 24 hours - ongoing monitoring of MH consumer length of stay (LOS) in ED
1.5.2 Actions are taken to minimise risks to patient safety and quality of care | Ensure that action is taken to minimise the risks to patient safety and quality of care by ensuring that the Ligature Audit recommendations are actioned, completed and documented with a report sent to all relevant areas of the completion of the recommendations in a timely manner.
| Continue to monitor compliance with ligature audit recommendations | 100% of Ligature audit recommendations are completed within required timeframe documented in Organisation wide instruction (OWI)
| Current risk 2411 in relation to ligature risk identification is revised to incorporate access to other methods of self harm | New risk developed and controls and treatments identified to address the risk and compliance monitored as per existing processes
| Incorporate into SSI03216 Ligature Point Audit: to include the requirement for all new equipment to have a ligature assessment. Frequency of auditing to be stipulated in OWI, | Safety audit reports and actions plans will include other risks for self harm not just ligature points
All the high risk recommendations have been adddressed
| The release of the OWI highlighting the changes to the OWI are communicated to staff | Safety audit reports and actions plans will include other risks for self harm not just ligature points
| Continue to review the treatments in risk 2356 follow up of mental health consumers 7 days post discharge - inpatient units | Timeframes for treatments are monitoring of the risk continue fortnightly
Ensure that a system for the capture and documentation of all 7-day patient follow-up post discharge is captured and evidence of the mechanisms put in place if a patient is unable to be contacted.
| Revise OWI03250 regarding 7 day post discharge follow up: to provide more specific requirements | Revised OWI:will include specific requirements regarding the 7 day post discharge follow up in relation to the requirements when consumer is transferred to another care facility
| The release of the OWI highlighting the changes to the OWI are communicated to staff | 7 day post discharge follow up rates maintained above National Target Rate of 60%
Service Managers will meet with NUMs once per week to examine weekly discharges (PAS data) and follow up compliance for each patient (manually on CBIS). Track via Service Managers meetings.
| Review CBIS data base to align different UR numbers for the same patient | CBIS data collection of 7 day post discharge follow up rate aligns with the audit data results
| 7 Day PDFU Working Group will be established and will recommend effective processes and strategies to improve follow up | 7 day post discharge follow up rate audit data achieves 90%
7 Day PDFU audits will confirm November 2017 compliance results that CALHN is achieving above the National Target Rate of 60%. Plan to re-audit 1st week of April

## Progress of MH Standard 4
Target for evaluation strategy
Has not commenced/ behind target
Progressing well, on target
Completed / target achieved
Recommendation | Planned Actions | Evaluation Strategy | Progress updates (fortnightly)
|  |  | 2018-03-23 | 2018-04-06 | 2018-04-20 | 2018-05-04 | 2018-05-18 | 2018-06-01 | 2018-06-15
4.2.1 The medication management system is regularly assessed | MSSA to be completed and a plan in place to address any deficits identified - to be reported to the Medication Safety Committee | Action plan to address deficits with specific timeframes allocated to strategies should be monitored by mediction safety and lack of compliance with timeframes escalated to exec quality governance
Decision to made if 3 separate MSSA's to be conducted for TQEH, MH, RAH and if MSSA is to be staggerred across the 3 sites
4.6.1 A best possible medication history is documented for each patient | Ensure that a best possible medication history is documented for each patient within the community file. CALHN MHS must implement a system to maintain medication documentation rates on an ongoing basis.
4.12.3 A current comprehensive list of medicines is provided to the receiving clinician during clinical handover | Working party to be formed under leadership of EDMS and a project plan developed to increase effectiveness of discharge communication. First strategy to address this recommendation is to ensure that a discharge summary is provided to a consumer at the time of discharge, with a final discharge summary to be provided to all relevant community providers AND the patient a maximum of 2 weeks post discharge. The CALHN procedure should be altered to reflect this. | Communication strategy developed to communicate the clinical impact of failure to provide discharge summary | E-mail sent to medical clincial leaders to provide patient with a written discharge summary ensuring it includes a medication summary Meeting held with Comms - incidents to be identified to use as case studies - aim for weekly comms
4.12.4 Ensure that action is taken to increase the proportion of receiving clinicians that are provided with a current, comprehensive list of medicines at discharge. | Working party to be formed under leadership of EDMS and a project plan developed to increase effectiveness of discharge communication. First strategy to address this recommendation is to ensure that a discharge summary is provided to a consumer at the time of discharge, with a final discharge summary to be provided to all relevant community providers AND the patient a maximum of 2 weeks post discharge. The CALHN procedure should be altered to reflect this. | Project plan to be developed by the working party with actions and timeframes | Team members being identified
Compliance with electronic discharge summary increased by 50%
Compliance with electronic discharge summary increased by 50%
Audit compliance of random sample of current medication list in Oacis discharge summary to achieve 50 % compliance with medication list
Audit compliance of random sample of current medication list in Oacis discharge summary to achieve 75 % compliance with medication list
| Plan is to be developed to outline the planned actions to be taken | Plan is developed outlining planned actions to be taken including responsibility and timeframes
| Business case to be developed for Clinical Pharmacy support for Community teams | Clinical pharmacists will be in place in community teams within 12 months
| Communicate the requirement to complete medrec with 3 monthly clinical reviews | Improve medrec completion rates by 50%

## Progress of MH Standard 6 (hidden)
Target for evaluation strategy
Has not commenced/ behind target
Progressing well, on target
Completed / target achieved
Recommendation | Planned Actions | Evaluation Strategy | Progress updates (fortnightly)
|  |  | 2018-03-23 | 2018-04-06 | 2018-04-20 | 2018-05-04 | 2018-05-18 | 2018-06-01 | 2018-06-15
6.3.3 Action is taken to increase the effectiveness of clinical handover | Action be taken to improve the discharge summary completion rate for patients whose care is being taken on wholly, or in part, by primary care or private health providers. That the service ensures that the completed discharge summary is provided to the appropriate health providers in a timely manner | Working party to be formed under leadership of EDMS and a project plan developed to increase effectiveness of discharge communication. First strategy to address this recommendation is to ensure that a discharge summary is provided to a consumer at the time of discharge, with a final discharge summary to be provided to all relevant community providers AND the patient a maximum of 2 weeks post discharge. The CALHN procedure should be altered to reflect this. | E-mail sent to medical clincial leaders to provide patient with a written discharge summary ensuring it includes a medication summary Team members being identified
CALHN discharge summary procedure to be updated that a discharge summary is provided to a consumer at the time of discharge, with a final discharge summary to be provided to all relevant community providers AND the patient a maximum of 2 weeks post discharge
Project plan to be developed by the working party with actions and timeframes
Compliance with electronic discharge summary increased by 50%
Compliance with electronic discharge summary increased by 75%
Audit compliance of random sample of current medication list in Oacis discharge summary to achieve 50 % compliance with medication list
Audit compliance of random sample of current medication list in Oacis discharge summary to achieve 75 % compliance with medication list

## Progress Standard 2 Safety (hidden)
Target for evaluation strategy
Has not commenced/ behind target
Progressing well, on target
Completed / target achieved
Recommendation | Planned Actions | Evaluation Strategy | Progress updates (fortnightly)
|  |  | 2018-03-23 | 2018-04-06 | 2018-04-20 | 2018-05-04 | 2018-05-18 | 2018-06-01 | 2018-06-15
2.2 The MHS reduces and where possible eliminates the use of restraint and seclusion within all MHS settings. | The MHD adhere to the Mental Health Act of South Australia 2009 and ensure all seclusion beds in CALHN are used for seclusion only. This recommendation is cross referenced to NSQHSS Recommendation - Action 1.2.2

## Progress Standard 4 Diversty (hidden)
Target for evaluation strategy
Has not commenced/ behind target
Progressing well, on target
Completed / target achieved
Recommendation | Planned Actions | Evaluation Strategy | Progress updates (fortnightly)
|  |  | 2018-03-23 | 2018-04-06 | 2018-04-20 | 2018-05-04 | 2018-05-18 | 2018-06-01 | 2018-06-15
4.5 Staff are trained to access information and resources to provide services that are appropriate to the diverse needs of its consumers. | Cultural awareness training be made available for all mental health services staff in 2018 and the attendance monitored and reported on, to ensure the MHS workforce are provided with appropriate knowledge and understanding of the diverse needs of the consumers in their care.

## Progress Standard 5 Promotion (hidden)
Target for evaluation strategy
Has not commenced/ behind target
Progressing well, on target
Completed / target achieved
Recommendation | Planned Actions | Evaluation Strategy | Progress updates (fortnightly)
|  |  | 2018-03-23 | 2018-04-06 | 2018-04-20 | 2018-05-04 | 2018-05-18 | 2018-06-01 | 2018-06-15
5.4 The MHS evaluates strategies, implementation plans, sustainability of partnerships and individual activities in consultation with their partners. Regular progress reports on achievements are provided to consumers, carers, other service providers and relevant stakeholders. | The MHS provide evidence of regular consultation and documented progress reporting to ensure the sustainability of all partnerships.
5.6 The MHS ensures that their workforce is adequately trained in the principles of mental health promotion and prevention and their applicability to the specialised mental health service context with appropriate support provided to implement mental health promotion and prevention activities | The MHS to include on the staff education calendar training in Mental Health Promotion and Prevention principles.

## Progress Standard 7 Carers (hidden)
Target for evaluation strategy
Has not commenced/ behind target
Progressing well, on target
Completed / target achieved
Recommendation | Planned Actions | Evaluation Strategy | Progress updates (fortnightly)
|  |  | 2018-03-23 | 2018-04-06 | 2018-04-20 | 2018-05-04 | 2018-05-18 | 2018-06-01 | 2018-06-15
7.2 The MHS implements and maintains ongoing engagement with carers as partners in the delivery of care as soon as possible in all episodes of care. | The CALHN MHD actively review the involvement of carers in consumer treatment and document in consumer care plans the engagement and level of carer involvement for the consumer.
7.11 The MHS actively encourages routine identification of carers in the development of relapse prevention plans. | Ensure there is a mechanism for carer input and feedback to support consumers in the development of their relapse prevention plans

## Progress Standard 10 del care (hidden)
Target for evaluation strategy
Has not commenced/ behind target
Progressing well, on target
Completed / target achieved
Recommendation | Planned Actions | Evaluation Strategy | Progress updates (fortnightly)
|  |  | 2018-03-23 | 2018-04-06 | 2018-04-20 | 2018-05-04 | 2018-05-18 | 2018-06-01 | 2018-06-15
10.6.1 The MHS ensures that on exiting the service the consumer has access to services that promote recovery and aim to minimise psychiatric disability and prevent relapse. | Ensure all information is sent to the General Practitioner (GP) or designated support service/s within the designated timelines as per policy and documented. | see NSQHS 6.3.3
10.6.8 The MHS, in conjunction with the treating clinician, has a procedure for appropriate follow-up of all consumers within 7 days after discharge from inpatient care wherever possible, and has a follow-up procedure for those consumers who do not keep the planned follow-up arrangements. | Ensure consumers receive a telephone call and clinical assessment within seven days of discharge and this is documented in CBIS seven-day PDFU section. Ensure unsuccessful attempts are escalated to the ward/ area/ unit Nurse Unit Manager and the Medical Head of Unit and ensure a continuing focus on those areas that did not meet the target rate of 60%. | see NSQHS 1.5.2